## Overview
Property superapp: brokerage launch and pilot roadmap
Phased plan to open a RERA-licensed brokerage, run a pilot in about 9-13 weeks, and raise funds. Change the yellow cell and every date recalculates.
Inputs
| Project start date (Monday) | 2026-10-12 | Working week assumed Monday to Friday. Weekend is Saturday and Sunday.
| Pilot go-live date | 2026-12-07 | From milestone M2 in the Roadmap.
| Weeks from start to pilot go-live | 9
Phase summary
| Phase | Goal | Start wk | End wk | Tasks | Done | % done | Cost AED
| P0 Validate | Prove the problem is real and the model is legal | 1 | 6 | 13 | 0 | 0% | 25500
| P1 Set up | Get licensed and operating | 2 | 8 | 17 | 0 | 0% | 93000
| P2 Pilot | Build, launch and run a small real pilot | 4 | 13 | 17 | 0 | 0% | 49000
| P3 Raise | Turn evidence into an investor round | 7 | 20 | 8 | 0 | 0% | 8000
| Total |  |  |  | 55 | 0 | 0% | 175500
Gate status
| Gate | Stage | Criteria | Met | Not met | Pending
| G0 | Week 6: problem and plan validated | 6 | 0 | 0 | 6
| G1 | Week 8: licensed and pilot-ready | 7 | 0 | 0 | 7
| G2 | Week 13: pilot proven | 6 | 0 | 0 | 6
| G3 | Week 19-20: term sheet or first close | 3 | 0 | 0 | 3
How to use this workbook
Roadmap: every task has an owner designation, a how-to, a deliverable and a cost estimate. Update Status weekly.
Gantt: a visual of the same plan, drawn by formula. Do not type in it.
Gates: four go / no-go checkpoints. Enter actual results in yellow cells.
Roles: designations used as owners, with placeholder salaries. Budget: rolls up cost to the funding gap.
Deck Storyline: slide-by-slide plan for the pitch deck, linked to the evidence you will collect.
Colour code: blue text = input you can change; black = formula; yellow fill = cells you fill in.
Compliance reminder: do not pay unlicensed people for introductions until the legal opinion (Roadmap 0.08) is in hand.
Dependencies matter: the licence (tasks 1.02 to 1.10) is the longest chain and sets the earliest pilot date. Fallback in task 1.17.

## Roadmap
Roadmap: step-by-step plan with owners and milestones
Blue = inputs you can change (start week, duration, cost, owner). Dates recalculate from the project start date on the Overview sheet.
ID | Phase | Workstream | Task / milestone | Type | How to complete (step by step) | Owner (designation) | Support | Start wk | Dur (wks) | End wk | Start date | End date | Depends on | Deliverable / evidence of done | Est. cost AED (excl. salaries) | Status | Notes / risk
0.01 | P0 Validate | Strategy | Define wedge, ideal customer and 3 core hypotheses | Task | 1) Pick one first customer (e.g. overseas buyer of AED 1-3m off-plan, or UAE first-time buyer). 2) Write the top 3 problems they have today. 3) List the hypotheses the survey must prove (see Survey workbook, H1-H10). 4) Decide what is in and out of the pilot. | Founder & CEO | Co-founder & CTO | 1 | 1 | 1 | 2026-10-12 | 2026-10-16 | - | One-page ICP and hypotheses | 0 | Not started
0.02 | P0 Validate | Legal | Founders agreement, vesting and IP assignment | Task | 1) Agree equity split and vesting (e.g. 4 years, 1 year cliff). 2) Sign IP assignment so all code, designs and data belong to the company. 3) Keep signed copies for the data room. | Founder & CEO | Legal Counsel | 1 | 2 | 2 | 2026-10-12 | 2026-10-23 | - | Signed founders agreement | 4000 | Not started | Estimate. Get a fixed-fee quote.
0.03 | P0 Validate | Evidence | Build the survey and test it with 5 people | Task | 1) Load the questionnaire from the Survey workbook into Google Forms or Typeform. 2) Add the consent text. 3) Test with 5 people, fix unclear questions, check it takes under 10 minutes. | Head of Growth | Data Analyst | 1 | 1 | 1 | 2026-10-12 | 2026-10-16 | 0.01 | Live survey link | 0 | Not started
0.04 | P0 Validate | Evidence | Run the survey: reach 300+ respondents (50% overseas) | Task | 1) Post in expat and investor WhatsApp, LinkedIn and Facebook groups and relevant subreddits. 2) Ask 20 friends to forward it. 3) Run AED 3,000 of targeted ads to overseas buyers. 4) Offer a small prize draw. 5) Track responses by segment weekly. | Head of Growth | Founder & CEO | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | 0.03 | 300+ responses, segment quotas met | 5000 | Not started | Ads AED 3,000 + incentive AED 2,000 (estimate).
0.05 | P0 Validate | Evidence | 30 depth interviews with buyers, investors and tenants | Task | 1) Recruit from survey respondents who opt in. 2) 30-40 minute calls using the interview guide (journey walk-through, last purchase, biggest frustration). 3) Record with consent, tag quotes by hypothesis. | Founder & CEO | Head of Growth | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | 0.03 | 30 interview notes and 10 strong quotes | 1500 | Not started | Incentives, estimate.
0.06 | P0 Validate | Evidence | Supply-side interviews: developers, brokerages, designers, furniture brands | Task | 1) Speak to 10 developer sales or channel heads, 5 brokerages, 5 interior designers or furniture brands. 2) Ask about commission, inventory access, online booking, 3D assets. 3) Ask each for a letter of intent. | Partnerships Lead (Developers & Supply) | Founder & CEO | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | 0.01 | 20 interviews logged | 0 | Not started
0.07 | P0 Validate | Evidence | Mystery-shop 6 competitors end to end | Task | 1) Go through the buyer journey on Oliva, Huspy, PRYPCO, Property Finder, one developer app and one large brokerage. 2) Screenshot every step, time it and list gaps. 3) Summarise in a 1-page comparison. | Head of Growth | Product Designer | 2 | 2 | 3 | 2026-10-19 | 2026-10-30 | - | Competitor teardown | 0 | Not started
0.08 | P0 Validate | Legal | Legal opinion: referral model, payments flow, 3D asset rights, data protection | Task | 1) Brief a UAE real estate and fintech lawyer with the model. 2) Ask specifically: can unlicensed residents be paid for introductions, what is the safest structure, can the brokerage route payments to developer escrow, and who owns 3D and floor plan assets. 3) Get the answer in writing. | Legal Counsel | Founder & CEO | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | - | Written legal opinion | 15000 | Not started | Estimate. Do not launch the resident referral track before this arrives.
0.09 | P0 Validate | Evidence | Analyse survey and build the problem evidence pack | Task | 1) Export responses into the Survey workbook Responses sheet. 2) Read the Analysis sheet for each hypothesis. 3) Pick the 5 strongest numbers and 5 quotes for the deck. 4) Note weak results honestly. | Data Analyst | Founder & CEO | 5 | 1 | 5 | 2026-11-09 | 2026-11-13 | 0.04, 0.05 | Evidence pack (charts and quotes) | 0 | Not started
0.10 | P0 Validate | Deck | Pitch deck v1: problem, market, solution, plan | Task | 1) Follow the Deck Storyline sheet slide by slide. 2) Lead with the problem and the survey numbers. 3) Keep to 12-15 slides. 4) Mark pilot-results slides as placeholders. | Founder & CEO | Head of Growth | 3 | 3 | 5 | 2026-10-26 | 2026-11-13 | 0.01 | Deck v1 PDF | 0 | Not started | Start the story in week 3, insert survey numbers in week 5.
0.11 | P0 Validate | Partnerships | Collect letters of intent: 3 developers, 1 designer, 1 furniture partner | Task | 1) Send a one-page LOI template (non-binding) after each interview. 2) Ask for commission rate, inventory access and 3D asset permission. 3) Follow up weekly. | Partnerships Lead (Developers & Supply) | Founder & CEO | 3 | 4 | 6 | 2026-10-26 | 2026-11-20 | 0.06 | 5 signed LOIs | 0 | Not started
0.12 | P0 Validate | Deck | Review deck v1 with 3-5 mentors or angels and revise | Task | 1) Send deck with a 3-question feedback form. 2) Hold 20-minute calls. 3) Revise story, numbers and ask. | Founder & CEO | - | 6 | 1 | 6 | 2026-11-16 | 2026-11-20 | 0.10 | Deck v1.1 | 0 | Not started
0.13 | P0 Validate | Gate | GATE G0: problem and plan validated | Gate | Review the G0 criteria in the Gates sheet. Go only if the survey, interviews, LOIs and legal opinion support the model. If not, adjust the wedge before spending on set-up. | Founder & CEO | Advisors | 6 | 1 | 6 | 2026-11-16 | 2026-11-20 | 0.09, 0.11, 0.08 | Go / no-go decision recorded | 0 | Not started
1.01 | P1 Set up | Company | Appoint setup consultant (PRO) and confirm entity route | Task | 1) Get 3 fixed-fee quotes. 2) Confirm a Dubai mainland company under DET with the real estate brokerage activity is the right route. 3) Agree scope: DET licence, RERA registration, Ejari, visas. | Founder & CEO | Business Setup Consultant / PRO | 2 | 1 | 2 | 2026-10-19 | 2026-10-23 | - | Signed engagement | 5000 | Not started | Estimate; some packages bundle this.
1.02 | P1 Set up | People | Hire a RERA-certified Broker-Manager | Task | 1) A licensed manager who has passed the RERA exam must be named for the firm. 2) Source from your network and brokerage recruiters. 3) Agree a role including equity or bonus tied to licence and pilot. | Founder & CEO | Advisors | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | - | Offer letter signed | 0 | Not started | Long lead item: start now.
1.03 | P1 Set up | People | Founder and manager complete RERA training (DREI CTREB course) and exam | Task | 1) Book the 4-5 day Certified Training for Real Estate Brokers at the Dubai Real Estate Institute. 2) Sit the RERA exam. 3) Keep certificates for the licence file. | Broker-Manager (Head of Brokerage) | Founder & CEO | 3 | 2 | 4 | 2026-10-26 | 2026-11-06 | 1.02 | Exam passed | 9000 | Not started | Estimate AED 3,000-4,500 per person; skip if already certified.
1.04 | P1 Set up | Company | Reserve trade name, draft MoA, get DET initial approval | Task | 1) Choose 3 name options. 2) Draft MoA with shareholders and the manager. 3) Submit for initial approval through the PRO. | Business Setup Consultant / PRO | Founder & CEO | 3 | 1 | 3 | 2026-10-26 | 2026-10-30 | 1.01 | Initial approval certificate | 0 | Not started
1.05 | P1 Set up | Company | Lease a physical office or serviced desk and register Ejari | Task | 1) RERA requires a real commercial address; virtual offices are not accepted. 2) Pick a flexi-desk or serviced office in a commercial building. 3) Get the tenancy contract and register Ejari. | Founder & CEO | Business Setup Consultant / PRO | 3 | 2 | 4 | 2026-10-26 | 2026-11-06 | 1.01 | Tenancy contract and Ejari | 25000 | Not started | Estimate AED 15,000-40,000 per year.
1.06 | P1 Set up | Company | Issue DET trade licence (real estate brokerage activity) | Task | 1) PRO submits MoA, lease and approvals. 2) Pay licence fees. 3) Collect licence and establishment card. | Business Setup Consultant / PRO | Founder & CEO | 4 | 2 | 5 | 2026-11-02 | 2026-11-13 | 1.04, 1.05 | Trade licence | 15000 | Not started | Estimate AED 12,000-15,000.
1.07 | P1 Set up | Finance | Open corporate bank account and deposit share capital | Task | 1) Start bank onboarding as soon as the licence is issued. 2) Deposit the minimum capital (starts at AED 100,000 for a standard brokerage). 3) Set up payment and card access. | Fractional CFO | Founder & CEO | 5 | 2 | 6 | 2026-11-09 | 2026-11-20 | 1.06 | Active bank account | 0 | Not started | Capital is not an expense; see Budget sheet.
1.08 | P1 Set up | Regulatory | Register the brokerage with RERA / DLD (Trakheesi) | Task | 1) Register the company as an authorised brokerage in Trakheesi once the DET licence is active and principals hold broker cards. 2) Pay the registration fee. 3) Get access to ad permits. | Broker-Manager (Head of Brokerage) | Business Setup Consultant / PRO | 5 | 2 | 6 | 2026-11-09 | 2026-11-20 | 1.03, 1.06 | RERA brokerage registration | 8000 | Not started | Estimate AED 5,000-10,000.
1.09 | P1 Set up | Regulatory | Issue broker cards for the manager and pilot agents | Task | 1) Each agent completes training and the exam. 2) Apply through Trakheesi under the firm. 3) Cards are valid for a set period and must be renewed. | Broker-Manager (Head of Brokerage) | Business Setup Consultant / PRO | 5 | 2 | 6 | 2026-11-09 | 2026-11-20 | 1.03 | At least 2 valid broker cards | 15000 | Not started | Estimate ~AED 5,000 per card.
1.10 | P1 Set up | Compliance | Register on goAML, appoint compliance officer, write AML/KYC policy | Task | 1) Brokers are DNFBPs under the UAE AML law. 2) Register on goAML. 3) Appoint a compliance officer. 4) Write a risk-based KYC policy: ID checks, source of funds, sanctions screening, reporting of cash AED 55,000+ and any virtual asset payment. | Compliance & AML Officer | Legal Counsel | 5 | 3 | 7 | 2026-11-09 | 2026-11-27 | 1.06 | goAML account and approved policy | 5000 | Not started | Estimate for policy drafting.
1.11 | P1 Set up | Compliance | Policies and templates: Forms A/B, commission agreements, T&Cs, privacy, complaints | Task | 1) Use RERA standard forms where required. 2) Draft customer T&Cs, privacy notice (PDPL), referral terms and complaints process. 3) Lawyer review. | Legal Counsel | Compliance & AML Officer | 5 | 3 | 7 | 2026-11-09 | 2026-11-27 | 0.08 | Approved template pack | 5000 | Not started | Estimate.
1.12 | P1 Set up | Compliance | Professional indemnity and trade insurance | Task | 1) Get 3 quotes. 2) Choose cover for errors and omissions and general liability. 3) Keep the certificate for developers and investors. | Fractional CFO | Broker-Manager (Head of Brokerage) | 6 | 2 | 7 | 2026-11-16 | 2026-11-27 | 1.06 | Insurance certificate | 6000 | Not started | Estimate.
1.13 | P1 Set up | Partnerships | Sign developer broker agreements (3-5) and get portal access | Task | 1) Convert LOIs into broker agreements. 2) Get access to sales portals and live price lists. 3) Confirm commission rate and payout timing in writing. | Partnerships Lead (Developers & Supply) | Broker-Manager (Head of Brokerage) | 5 | 4 | 8 | 2026-11-09 | 2026-12-04 | 0.11, 1.08 | 3+ signed agreements | 0 | Not started | Needs RERA registration to finish.
1.14 | P1 Set up | Operations | Payment flow: route to developer escrow / trustee, brokerage never holds client funds | Task | 1) Map each payment type (booking, instalments, DLD fee, trustee fee). 2) Confirm with the lawyer who holds what. 3) Pick a licensed payment partner for platform fees only. | Founder & CEO | Legal Counsel | 6 | 2 | 7 | 2026-11-16 | 2026-11-27 | 0.08 | Approved payment flow diagram | 0 | Not started
1.15 | P1 Set up | Operations | Set up Trakheesi permit and Madmoun QR workflow for pilot listings | Task | 1) Create one permit per listed unit. 2) Add the QR to every ad and unit page. 3) Delist within 3 working days of a sale or rental. | Broker-Manager (Head of Brokerage) | Co-founder & CTO | 7 | 1 | 7 | 2026-11-23 | 2026-11-27 | 1.08 | Permit workflow tested | 0 | Not started
1.16 | P1 Set up | Milestone | MILESTONE M1: brokerage licensed and operating | Milestone | DET licence issued, RERA registration done, broker cards held, goAML registered. If not done by week 8, trigger task 1.17. | Founder & CEO | Broker-Manager (Head of Brokerage) | 8 | 1 | 8 | 2026-11-30 | 2026-12-04 | 1.06, 1.08, 1.09, 1.10 | Licence pack in data room | 0 | Not started
1.17 | P1 Set up | Contingency | If licence is late: run the pilot through a licensed partner brokerage | Task | 1) Decision point at week 8. 2) Only after the lawyer confirms the structure, run the pilot as co-brokerage with a licensed firm. 3) Move to your own licence once issued. | Founder & CEO | Legal Counsel | 8 | 1 | 8 | 2026-11-30 | 2026-12-04 | 1.16 | Decision recorded | 0 | Not started | Fallback to protect the pilot date.
2.01 | P2 Pilot | Product | Define pilot scope, target segment and success metrics | Task | 1) Choose 1 segment and 3 developers. 2) Set targets (see G2 in the Gates sheet). 3) Decide what is manual behind the scenes. | Founder & CEO | Head of Growth | 5 | 1 | 5 | 2026-11-09 | 2026-11-13 | 0.13 | Pilot charter | 0 | Not started
2.02 | P2 Pilot | Product | Clickable prototype of the core journey (insights, 3D, reserve, tracker) | Task | 1) Design 12-15 screens in Figma. 2) Link them into a clickable flow. 3) Use it in investor and user meetings. | Co-founder & CTO | Product Designer | 4 | 3 | 6 | 2026-11-02 | 2026-11-20 | 0.01 | Figma prototype | 6000 | Not started | Estimate.
2.03 | P2 Pilot | Product | Test the prototype with 10 users and iterate | Task | 1) Run 30-minute sessions. 2) Measure task success and time. 3) Fix the top 5 issues. | Product Designer | Head of Growth | 7 | 1 | 7 | 2026-11-23 | 2026-11-27 | 2.02 | Test report | 0 | Not started
2.04 | P2 Pilot | Product | Insights v0: data sources and 5 insight cards | Task | 1) Source Dubai Land Department open data and get a quote for a licensed data feed. 2) Build 5 cards: price per sq ft trend, rental yield, supply pipeline, developer delivery record, service charge. 3) Show data source and date on every card. | Data Analyst | Co-founder & CTO | 5 | 4 | 8 | 2026-11-09 | 2026-12-04 | 0.01 | 5 live insight cards | 10000 | Not started | Estimate for data licence.
2.05 | P2 Pilot | Product | 3D / virtual tour for 10 units via developer assets or a viewer partner | Task | 1) Ask developers for their 3D and floor plan files. 2) Get written permission to display them. 3) Embed a viewer. 4) Do not build in-house 3D for the pilot. | Partnerships Lead (Developers & Supply) | Co-founder & CTO | 6 | 3 | 8 | 2026-11-16 | 2026-12-04 | 1.13 | 10 units with 3D view and signed asset permission | 8000 | Not started | Estimate.
2.06 | P2 Pilot | Product | Documents and payment reminders v0 | Task | 1) Build a checklist per deal type (off-plan, ready, rent). 2) Add a document vault. 3) Send reminders for instalments and registrations by email or WhatsApp. 4) Use no-code tools and a contractor first. | Co-founder & CTO | Product Designer | 6 | 3 | 8 | 2026-11-16 | 2026-12-04 | 0.01 | Working tracker for 5 test deals | 12000 | Not started | Estimate.
2.07 | P2 Pilot | Partnerships | Furniture and interior designer pilot with 1 designer and 1 retailer | Task | 1) Agree an affiliate or booking-fee deal. 2) Add a simple "design my unit" request form. 3) Do not build augmented reality design tools yet. | Partnerships Lead (Developers & Supply) | Co-founder & CTO | 7 | 3 | 9 | 2026-11-23 | 2026-12-11 | 0.11 | Partner terms and landing page | 2000 | Not started | Estimate.
2.08 | P2 Pilot | Growth | Referral programme v0 (licensed referrers only; residents only if the legal opinion allows) | Task | 1) Write referral rules, tracking links and payout timing. 2) Pay only licensed agents or as confirmed by the lawyer. 3) Add a path to become licensed through your firm. | Broker-Manager (Head of Brokerage) | Legal Counsel | 6 | 3 | 8 | 2026-11-16 | 2026-12-04 | 0.08 | Referral terms and tracking | 3000 | Not started | Estimate. Compliance critical.
2.09 | P2 Pilot | Operations | Operations playbook: enquiry to KYC to reservation to SPA to Oqood to tracker | Task | 1) Write the step list with who does what and how long each takes. 2) Add a checklist for every handover. 3) Practise on test deals. | Broker-Manager (Head of Brokerage) | Compliance & AML Officer | 6 | 3 | 8 | 2026-11-16 | 2026-12-04 | 1.11 | SOP document | 0 | Not started
2.10 | P2 Pilot | Growth | Recruit pilot cohort: 150 sign-ups, 5-10 referrers, 150+ units live | Task | 1) Invite opted-in survey respondents. 2) Onboard referrers. 3) Load units from signed developers with permits. | Head of Growth | Partnerships Lead (Developers & Supply) | 7 | 2 | 8 | 2026-11-23 | 2026-12-04 | 0.04, 1.13 | Cohort list | 0 | Not started
2.11 | P2 Pilot | Product | Weekly KPI dashboard: leads, reservations, CAC, NPS | Task | 1) Track sign-ups, qualified leads, reservations, SPA signed, CAC and NPS. 2) Refresh every Monday. 3) Share with advisors. | Data Analyst | Head of Growth | 8 | 1 | 8 | 2026-11-30 | 2026-12-04 | 2.01 | Dashboard live | 0 | Not started
2.12 | P2 Pilot | Operations | Internal dry run: 5 end-to-end test journeys | Task | 1) Run 5 mock deals through KYC, reservation, documents and reminders. 2) Fix breakages. 3) Sign off compliance. | Broker-Manager (Head of Brokerage) | Co-founder & CTO | 8 | 1 | 8 | 2026-11-30 | 2026-12-04 | 1.16, 2.06 | Dry-run report | 0 | Not started
2.13 | P2 Pilot | Gate | GATE G1: pilot-ready decision | Gate | Check G1 criteria in the Gates sheet. Go live only if licensed, developers signed and dry run passed. | Founder & CEO | Advisors | 8 | 1 | 8 | 2026-11-30 | 2026-12-04 | 1.16, 2.12 | Go-live approved | 0 | Not started
2.14 | P2 Pilot | Milestone | MILESTONE M2: pilot go-live | Milestone | Open the pilot to the cohort with real inventory and real transactions. | Founder & CEO | Head of Growth | 9 | 1 | 9 | 2026-12-07 | 2026-12-11 | 2.13 | Pilot live | 0 | Not started
2.15 | P2 Pilot | Operations | Run the pilot with weekly KPI review | Task | 1) Weekly 30-minute review of KPIs and user feedback. 2) Fix the top issue each week. 3) Log every closed deal with commission received. | Founder & CEO | Head of Growth | 9 | 5 | 13 | 2026-12-07 | 2027-01-08 | 2.14 | 5 weekly KPI reports | 8000 | Not started | Marketing budget, estimate.
2.16 | P2 Pilot | Evidence | Capture testimonials, case studies and partner confirmations | Task | 1) Ask each pilot customer for a short quote and permission. 2) Write 2 case studies. 3) Get developers to confirm results in an email. | Partnerships Lead (Developers & Supply) | Head of Growth | 11 | 3 | 13 | 2026-12-21 | 2027-01-08 | 2.14 | 2 case studies, 5 quotes | 0 | Not started
2.17 | P2 Pilot | Gate | GATE G2: pilot proven | Gate | Compare actual pilot results with targets in the Gates sheet. Present to advisors. | Founder & CEO | Advisors | 13 | 1 | 13 | 2027-01-04 | 2027-01-08 | 2.15 | Pilot results report | 0 | Not started
3.01 | P3 Raise | Fundraising | Investor target list (50) and warm-introduction map; apply to startup programmes | Task | 1) List angels, seed funds and strategic investors active in UAE proptech. 2) Map warm intros through advisors and founders. 3) Apply to local accelerators or support programmes. | Founder & CEO | - | 7 | 2 | 8 | 2026-11-23 | 2026-12-04 | 0.12 | Investor CRM sheet | 0 | Not started
3.02 | P3 Raise | Fundraising | Three-year monthly financial model and use of funds | Task | 1) Build from pilot unit economics. 2) Show revenue by stream, CAC, margin and runway. 3) State the raise and the milestones it funds. | Fractional CFO | Founder & CEO | 8 | 3 | 10 | 2026-11-30 | 2026-12-18 | 2.11 | Financial model (xlsx) | 0 | Not started
3.03 | P3 Raise | Fundraising | Cap table, funding instrument (SAFE or equity), ESOP and legal readiness | Task | 1) Choose instrument and valuation range. 2) Set up the cap table. 3) Prepare standard documents. | Legal Counsel | Fractional CFO | 9 | 2 | 10 | 2026-12-07 | 2026-12-18 | 0.02 | Investment-ready legal pack | 8000 | Not started | Estimate.
3.04 | P3 Raise | Fundraising | Build the data room | Task | 1) Folders: company, licences, legal opinion, LOIs, survey data, pilot data, model, cap table, IP. 2) Keep access logs. 3) Update weekly. | Founder & CEO | Fractional CFO | 10 | 3 | 12 | 2026-12-14 | 2027-01-01 | 1.16 | Data room link | 0 | Not started
3.05 | P3 Raise | Deck | Pitch deck v2 with pilot results | Task | 1) Replace placeholders with real pilot numbers. 2) Add case studies and quotes. 3) Rehearse a 10-minute pitch and a 5-minute version. | Founder & CEO | Head of Growth | 12 | 2 | 13 | 2026-12-28 | 2027-01-08 | 2.17 | Deck v2 | 0 | Not started
3.06 | P3 Raise | Fundraising | Investor outreach and first meetings | Task | 1) Send 10 intros a week. 2) Book 25 first meetings. 3) Track feedback and objections. | Founder & CEO | - | 12 | 5 | 16 | 2026-12-28 | 2027-01-29 | 3.05 | 25 meetings held | 0 | Not started
3.07 | P3 Raise | Fundraising | Follow-ups and due diligence responses | Task | 1) Reply within 24 hours. 2) Share data room access. 3) Negotiate terms with the lawyer. | Founder & CEO | Fractional CFO | 15 | 4 | 18 | 2027-01-18 | 2027-02-12 | 3.06 | Diligence closed | 0 | Not started
3.08 | P3 Raise | Gate | GATE G3: term sheet or first close | Gate | Check G3 criteria in the Gates sheet. | Founder & CEO | Legal Counsel | 19 | 2 | 20 | 2027-02-15 | 2027-02-26 | 3.07 | Term sheet signed | 0 | Not started
|  |  | Total est. cost (third-party and government fees) | [11 empty] | 175500
Cost figures are estimates from published ranges (see Sources) and must be replaced with quotes.
Formulas:
Start date = Overview!$C5+([Start wk]-1)*7
End date = [Start date]+([Dur (wks)]-1)*7+4

## Gantt
Gantt: 20-week view
Bars are drawn by formula from Start wk and Dur on the Roadmap sheet. Colour = phase.
[5 empty] | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
ID | Phase | Task | Owner | Start wk | End wk | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22
0.01 | P0 Validate | Define wedge, ideal customer and 3 core hypotheses | Founder & CEO | 1 | 1 | 1
0.02 | P0 Validate | Founders agreement, vesting and IP assignment | Founder & CEO | 1 | 2 | 1 | 1
0.03 | P0 Validate | Build the survey and test it with 5 people | Head of Growth | 1 | 1 | 1
0.04 | P0 Validate | Run the survey: reach 300+ respondents (50% overseas) | Head of Growth | 2 | 4 |  | 1 | 1 | 1
0.05 | P0 Validate | 30 depth interviews with buyers, investors and tenants | Founder & CEO | 2 | 4 |  | 1 | 1 | 1
0.06 | P0 Validate | Supply-side interviews: developers, brokerages, designers, furniture brands | Partnerships Lead (Developers & Supply) | 2 | 4 |  | 1 | 1 | 1
0.07 | P0 Validate | Mystery-shop 6 competitors end to end | Head of Growth | 2 | 3 |  | 1 | 1
0.08 | P0 Validate | Legal opinion: referral model, payments flow, 3D asset rights, data protection | Legal Counsel | 2 | 4 |  | 1 | 1 | 1
0.09 | P0 Validate | Analyse survey and build the problem evidence pack | Data Analyst | 5 | 5 |  |  |  |  | 1
0.10 | P0 Validate | Pitch deck v1: problem, market, solution, plan | Founder & CEO | 3 | 5 |  |  | 1 | 1 | 1
0.11 | P0 Validate | Collect letters of intent: 3 developers, 1 designer, 1 furniture partner | Partnerships Lead (Developers & Supply) | 3 | 6 |  |  | 1 | 1 | 1 | 1
0.12 | P0 Validate | Review deck v1 with 3-5 mentors or angels and revise | Founder & CEO | 6 | 6 | [5 empty] | 1
0.13 | P0 Validate | GATE G0: problem and plan validated | Founder & CEO | 6 | 6 | [5 empty] | 1
1.01 | P1 Set up | Appoint setup consultant (PRO) and confirm entity route | Founder & CEO | 2 | 2 |  | 1
1.02 | P1 Set up | Hire a RERA-certified Broker-Manager | Founder & CEO | 2 | 4 |  | 1 | 1 | 1
1.03 | P1 Set up | Founder and manager complete RERA training (DREI CTREB course) and exam | Broker-Manager (Head of Brokerage) | 3 | 4 |  |  | 1 | 1
1.04 | P1 Set up | Reserve trade name, draft MoA, get DET initial approval | Business Setup Consultant / PRO | 3 | 3 |  |  | 1
1.05 | P1 Set up | Lease a physical office or serviced desk and register Ejari | Founder & CEO | 3 | 4 |  |  | 1 | 1
1.06 | P1 Set up | Issue DET trade licence (real estate brokerage activity) | Business Setup Consultant / PRO | 4 | 5 |  |  |  | 1 | 1
1.07 | P1 Set up | Open corporate bank account and deposit share capital | Fractional CFO | 5 | 6 |  |  |  |  | 1 | 1
1.08 | P1 Set up | Register the brokerage with RERA / DLD (Trakheesi) | Broker-Manager (Head of Brokerage) | 5 | 6 |  |  |  |  | 1 | 1
1.09 | P1 Set up | Issue broker cards for the manager and pilot agents | Broker-Manager (Head of Brokerage) | 5 | 6 |  |  |  |  | 1 | 1
1.10 | P1 Set up | Register on goAML, appoint compliance officer, write AML/KYC policy | Compliance & AML Officer | 5 | 7 |  |  |  |  | 1 | 1 | 1
1.11 | P1 Set up | Policies and templates: Forms A/B, commission agreements, T&Cs, privacy, complaints | Legal Counsel | 5 | 7 |  |  |  |  | 1 | 1 | 1
1.12 | P1 Set up | Professional indemnity and trade insurance | Fractional CFO | 6 | 7 | [5 empty] | 1 | 1
1.13 | P1 Set up | Sign developer broker agreements (3-5) and get portal access | Partnerships Lead (Developers & Supply) | 5 | 8 |  |  |  |  | 1 | 1 | 1 | 1
1.14 | P1 Set up | Payment flow: route to developer escrow / trustee, brokerage never holds client funds | Founder & CEO | 6 | 7 | [5 empty] | 1 | 1
1.15 | P1 Set up | Set up Trakheesi permit and Madmoun QR workflow for pilot listings | Broker-Manager (Head of Brokerage) | 7 | 7 | [6 empty] | 1
1.16 | P1 Set up | MILESTONE M1: brokerage licensed and operating | Founder & CEO | 8 | 8 | [7 empty] | 1
1.17 | P1 Set up | If licence is late: run the pilot through a licensed partner brokerage | Founder & CEO | 8 | 8 | [7 empty] | 1
2.01 | P2 Pilot | Define pilot scope, target segment and success metrics | Founder & CEO | 5 | 5 |  |  |  |  | 1
2.02 | P2 Pilot | Clickable prototype of the core journey (insights, 3D, reserve, tracker) | Co-founder & CTO | 4 | 6 |  |  |  | 1 | 1 | 1
2.03 | P2 Pilot | Test the prototype with 10 users and iterate | Product Designer | 7 | 7 | [6 empty] | 1
2.04 | P2 Pilot | Insights v0: data sources and 5 insight cards | Data Analyst | 5 | 8 |  |  |  |  | 1 | 1 | 1 | 1
2.05 | P2 Pilot | 3D / virtual tour for 10 units via developer assets or a viewer partner | Partnerships Lead (Developers & Supply) | 6 | 8 | [5 empty] | 1 | 1 | 1
2.06 | P2 Pilot | Documents and payment reminders v0 | Co-founder & CTO | 6 | 8 | [5 empty] | 1 | 1 | 1
2.07 | P2 Pilot | Furniture and interior designer pilot with 1 designer and 1 retailer | Partnerships Lead (Developers & Supply) | 7 | 9 | [6 empty] | 1 | 1 | 1
2.08 | P2 Pilot | Referral programme v0 (licensed referrers only; residents only if the legal opinion allows) | Broker-Manager (Head of Brokerage) | 6 | 8 | [5 empty] | 1 | 1 | 1
2.09 | P2 Pilot | Operations playbook: enquiry to KYC to reservation to SPA to Oqood to tracker | Broker-Manager (Head of Brokerage) | 6 | 8 | [5 empty] | 1 | 1 | 1
2.10 | P2 Pilot | Recruit pilot cohort: 150 sign-ups, 5-10 referrers, 150+ units live | Head of Growth | 7 | 8 | [6 empty] | 1 | 1
2.11 | P2 Pilot | Weekly KPI dashboard: leads, reservations, CAC, NPS | Data Analyst | 8 | 8 | [7 empty] | 1
2.12 | P2 Pilot | Internal dry run: 5 end-to-end test journeys | Broker-Manager (Head of Brokerage) | 8 | 8 | [7 empty] | 1
2.13 | P2 Pilot | GATE G1: pilot-ready decision | Founder & CEO | 8 | 8 | [7 empty] | 1
2.14 | P2 Pilot | MILESTONE M2: pilot go-live | Founder & CEO | 9 | 9 | [8 empty] | 1
2.15 | P2 Pilot | Run the pilot with weekly KPI review | Founder & CEO | 9 | 13 | [8 empty] | 1 | 1 | 1 | 1 | 1
2.16 | P2 Pilot | Capture testimonials, case studies and partner confirmations | Partnerships Lead (Developers & Supply) | 11 | 13 | [10 empty] | 1 | 1 | 1
2.17 | P2 Pilot | GATE G2: pilot proven | Founder & CEO | 13 | 13 | [12 empty] | 1
3.01 | P3 Raise | Investor target list (50) and warm-introduction map; apply to startup programmes | Founder & CEO | 7 | 8 | [6 empty] | 1 | 1
3.02 | P3 Raise | Three-year monthly financial model and use of funds | Fractional CFO | 8 | 10 | [7 empty] | 1 | 1 | 1
3.03 | P3 Raise | Cap table, funding instrument (SAFE or equity), ESOP and legal readiness | Legal Counsel | 9 | 10 | [8 empty] | 1 | 1
3.04 | P3 Raise | Build the data room | Founder & CEO | 10 | 12 | [9 empty] | 1 | 1 | 1
3.05 | P3 Raise | Pitch deck v2 with pilot results | Founder & CEO | 12 | 13 | [11 empty] | 1 | 1
3.06 | P3 Raise | Investor outreach and first meetings | Founder & CEO | 12 | 16 | [11 empty] | 1 | 1 | 1 | 1 | 1
3.07 | P3 Raise | Follow-ups and due diligence responses | Founder & CEO | 15 | 18 | [14 empty] | 1 | 1 | 1 | 1
3.08 | P3 Raise | GATE G3: term sheet or first close | Founder & CEO | 19 | 20 | [18 empty] | 1 | 1

## Gates
Gates: investor-facing go / no-go criteria
Targets are suggestions (blue). Enter actual results in the yellow cells; Status updates by formula.
Gate | Stage | Criterion | Test | Target | Actual (enter) | Status | Evidence source
G0 | Week 6: problem and plan validated | Survey responses collected | >= | 300 |  | Pending | Survey export row count
G0 | Week 6: problem and plan validated | Respondents rating reliable information or verification as hard (4-5), % | >= | 60% |  | Pending | Survey Analysis sheet, H1
G0 | Week 6: problem and plan validated | Depth interviews completed | >= | 30 |  | Pending | Interview notes
G0 | Week 6: problem and plan validated | Letters of intent from developers | >= | 3 |  | Pending | Signed LOIs
G0 | Week 6: problem and plan validated | Written legal opinion received (1 = yes) | >= | 1 |  | Pending | Law firm letter
G0 | Week 6: problem and plan validated | Mentors who reviewed deck v1 | >= | 3 |  | Pending | Feedback forms
G1 | Week 8: licensed and pilot-ready | DET trade licence issued (1 = yes) | >= | 1 |  | Pending | Licence copy
G1 | Week 8: licensed and pilot-ready | RERA brokerage registration done (1 = yes) | >= | 1 |  | Pending | Trakheesi record
G1 | Week 8: licensed and pilot-ready | Valid broker cards held | >= | 2 |  | Pending | Card copies
G1 | Week 8: licensed and pilot-ready | goAML registered, AML policy approved (1 = yes) | >= | 1 |  | Pending | goAML confirmation
G1 | Week 8: licensed and pilot-ready | Signed developer agreements | >= | 3 |  | Pending | Agreements
G1 | Week 8: licensed and pilot-ready | Units live with permits | >= | 150 |  | Pending | Inventory sheet
G1 | Week 8: licensed and pilot-ready | Dry-run journeys passed | >= | 5 |  | Pending | Dry-run report
G2 | Week 13: pilot proven | Pilot sign-ups | >= | 150 |  | Pending | Dashboard
G2 | Week 13: pilot proven | Qualified leads | >= | 40 |  | Pending | Dashboard
G2 | Week 13: pilot proven | Reservations or bookings | >= | 10 |  | Pending | Dashboard
G2 | Week 13: pilot proven | SPAs or tenancy contracts signed | >= | 5 |  | Pending | Dashboard
G2 | Week 13: pilot proven | Pilot NPS (-100 to 100) | >= | 40 |  | Pending | Pilot survey
G2 | Week 13: pilot proven | Cost per qualified lead, AED | <= | 500 |  | Pending | Dashboard
G3 | Week 19-20: term sheet or first close | First investor meetings held | >= | 25 |  | Pending | Investor CRM
G3 | Week 19-20: term sheet or first close | Second meetings | >= | 8 |  | Pending | Investor CRM
G3 | Week 19-20: term sheet or first close | Term sheets received | >= | 1 |  | Pending | Investor CRM
Example (not counted): Survey responses collected; Target 300; Actual 312 -> Status shows "Met".

## Roles
Roles and owners
Owner designations used in the Roadmap. Salaries are placeholders (assumptions) to be replaced with real quotes. External firms are costed in Roadmap tasks, not here.
Designation | Type | Key responsibilities | Must hold | Needed from week | Monthly cost AED (assumption) | Months in plan (to wk 13) | Total AED
Founder & CEO | Founder | Vision, fundraising, investor relations, legal/entity decisions, final owner of pitch deck and gates | Broker card if acting as licensed manager (optional) | 1 | 0 | 3 | 0
Co-founder & CTO | Founder | Product, tech architecture, MVP build, data and security | - | 1 | 0 | 3 | 0
Broker-Manager (Head of Brokerage) | Hire | Licensed manager named on the RERA registration; runs deals, agent compliance, Form A/B/F handling, Trakheesi permits | RERA broker card + passed RERA exam (CTREB) | 2 | 22000 | 3 | 66000
Compliance & AML Officer | Fractional hire | goAML registration, KYC/AML policy, suspicious transaction and cash (AED 55k+) reporting, PDPL data protection | AML/CFT training; registered with MoET as DNFBP | 5 | 6000 | 3 | 18000
Head of Growth | Hire | Survey, lead generation, referral programme, paid and community channels, CAC tracking | - | 1 | 12000 | 3 | 36000
Partnerships Lead (Developers & Supply) | Hire | Developer agreements, inventory feeds, 3D asset rights, designer and furniture partners | - | 2 | 15000 | 3 | 45000
Product Designer | Freelance | Prototype, user tests, UI for insights, 3D viewer, tracker | - | 4 | 8000 | 2 | 16000
Data Analyst | Freelance / part-time | Survey analysis, insights engine v0, pilot KPI dashboard | - | 5 | 8000 | 3 | 24000
Fractional CFO | Fractional | Budget, financial model, cap table, data room, investor Q&A | - | 7 | 5000 | 3 | 15000
Licensed Sales Agents (x2) | Hire (pilot) | Close pilot deals under the brokerage; follow scripts and compliance rules | RERA broker card each | 8 | 10000 | 2 | 20000
Legal Counsel | External law firm | Legal opinion on referral model and payments flow, templates, T&Cs, PDPL, cap table docs | UAE-qualified | 2 | 0 | 0 | 0
Business Setup Consultant / PRO | External | DET trade licence, RERA registration, Ejari, visas, government portals | - | 2 | 0 | 0 | 0
[6 empty] | Total people cost | 240000
Assumption: founders take no salary during the pilot. Replace with your own numbers; blue = input.

## Budget
Budget to reach pilot results and investor outreach
Estimates only. Blue = input. Replace with quotes. Salaries come from the Roles sheet; third-party costs come from the Roadmap sheet.
Line | AED | Basis
A. Third-party and government costs by phase
P0 Validate | 25500 | Roadmap sheet
P1 Set up | 93000 | Roadmap sheet: licence, office, cards, insurance
P2 Pilot | 49000 | Roadmap sheet: product, data, marketing
P3 Raise | 8000 | Roadmap sheet: legal
Subtotal A | 175500
B. People costs (to week 13) | 240000 | Roles sheet
C. Contingency rate | 15% | Assumption: 15% of A + B
Contingency amount | 62325
Operating cash needed (A + B + contingency) | 477825
D. Share capital to deposit (not an expense) | 100000 | Source: minimum capital for a standard RERA brokerage starts at AED 100,000 (Takween Advisory). Confirm with your PRO.
Total cash to have available | 577825
Funds already committed by founders (enter) | 0 | Enter your own number
Funding gap | 577825 | Amount to bridge before or through the raise
Funding gap in USD (at 3.6725) | 157338.3254 | AED is pegged to USD at 3.6725

## Deck Storyline
Pitch deck storyline
Problem-first. Each slide lists the evidence it needs and where that evidence comes from in this plan.
Slide | Title | Key message | Evidence needed and source | Owner | Draft by week | Status
1 | Cover and one-liner | One sentence: what you do, for whom, and the outcome. | Name, logo, one-liner, contact | Founder | 3 | Not started
2 | The problem | Buying property in the UAE is slow, opaque and risky, especially for overseas buyers. Show 3 pains with numbers. | Survey: H1 reliable information, H2 inaccurate listings, H3 hidden costs, H4 paperwork; 5 quotes | Founder | 5 | Not started
3 | Who feels it | Name the first customer and show how many there are. | Survey segments; DLD data: foreign buyers 85-88% of transactions; buyer origins | Head of Growth | 5 | Not started
4 | Why now | Digital transfer is live (DLD Digital Sale, ADREC digital journey), record volumes, new broker rules. | DLD and ADREC announcements; market volumes 2025 and H1 2026 | Founder | 4 | Not started
5 | The solution | One app and one accountable company from research to keys. | Journey map; one-page flow diagram | Founder | 4 | Not started
6 | The product | Screens: insights, 3D view, document and payment tracker, design and furniture. | Figma prototype (Roadmap 2.02); user test result (2.03) | Co-founder & CTO | 7 | Not started
7 | How we make money | Developer commission 3-7%, resale 2% fee, mortgage referral, furniture and design, B2B data. Show unit economics for one deal. | Earlier research brief; pilot actual commission (Roadmap 2.15) | Fractional CFO | 9 | Not started
8 | Market size | Top-down and bottom-up. Fee pool vs total transaction value. | Earlier research brief: TAM, SAM, SOM | Fractional CFO | 8 | Not started
9 | Traction and pilot results | Waitlist, LOIs, pilot KPIs, quotes, case studies. | Gates G0 and G2; Roadmap 2.16 | Founder | 12 | Not started
10 | Go-to-market and referral engine | How customers arrive, why the referral network is compliant and scalable. | Survey G section (willingness to refer); legal opinion (Roadmap 0.08); referral terms (2.08) | Head of Growth | 12 | Not started
11 | Competition and edge | Honest map of portals, Huspy, PRYPCO, Oliva; what you do that they do not. | Mystery-shop teardown (Roadmap 0.07) | Founder | 6 | Not started
12 | Regulation and risk | Licensed brokerage, AML, escrow routing, data protection. Investors worry most about this slide. | Licence pack (M1), goAML, payment flow (1.14), insurance | Compliance & AML Officer | 9 | Not started
13 | Team and advisors | Why this team wins: licence holder, tech, partnerships, advisors. | Roles sheet | Founder | 6 | Not started
14 | Financials and milestones | 3-year view and the milestones the money buys. | Financial model (Roadmap 3.02); Budget sheet | Fractional CFO | 12 | Not started
15 | The ask and use of funds | Amount, instrument, runway, what it unlocks. | Budget sheet; Gate G3 | Founder | 12 | Not started
16 | Appendix | Survey detail, interview themes, legal summary, product roadmap. | Survey workbook; data room | Founder | 12 | Not started

## Sources
Sources and assumptions
Research current at October 2026. Fees and rules change; confirm with DLD, RERA and your setup consultant.
Used for | Source | Link
Broker licence steps, trade licence, RERA registration, office rule, fees | Oliva: Dubai real estate brokerage regulations 2026 | https://joinoliva.com/en/learn/blog/dubai-real-estate-brokerage-regulations-2026
Broker card fees, DREI CTREB course, RERA registration, minimum capital AED 100,000 | Takween Advisory: How to get a RERA licence in Dubai | https://takweenadvisory.ae/en/blog/how-to-get-rera-license-dubai
Cost ranges for opening a brokerage | Shuraa: Cost of opening a real estate brokerage in Dubai | https://www.shuraa.com/blog/2019/07/what-is-the-cost-of-opening-a-real-estate-brokerage-in-dubai.html
Broker obligations and code of ethics | Afridi & Angell: Responsibilities and Code of Ethics for Real Estate Brokers | https://afridi-angell.com/wp-content/uploads/2026/01/inBrief-Responsibilities-and-Code-of-Ethics-for-Real-Estate-Brokers-in-Dubai.pdf
AML duties for brokers, goAML, AED 55,000 cash reporting | AML UAE: AML regulations for DNFBPs in UAE | https://amluae.com/aml-regulations-for-dnfbps-in-uae/
DLD Digital Sale service | Dubai Land Department: Buy or sell property via DubaiNow | https://dubailand.gov.ae/en/eservices/buy-or-sell-property-via-dubai-now/
ADREC digital journey | WAM: ADREC launches Digital Buy & Sell Journey | https://www.wam.ae/en/article/bm6n7kr-adrec-launches-digital-buy-sell-journey
Estimates marked "Estimate" in the Roadmap and Roles sheets | Planning assumptions by the author; replace with quotes and real salaries | -